## Project Status
[8 empty] | Date: | 2022-03-29 18:46
| Professional Therapies System Upgrade | [6 empty] | Billing rate: | 85
| Project Status Report | [7 empty] | Consultants
Everett Hospital | Service ID | Service Description | Actual Hours | Actual $ | Estimated $ | Remaining $ | Remaining % |  | Name | Services | Manager | Years | Role | Eval Score
| G-131 | General administrative | 25 | 2125 | 2500 | 375 | 15% |  | Kirk Deegan | F-125 | Cisneros | 4.5 | Lead | 88
| G-240 | HIPAA compliance | 100 | 8500 | 8000 | -500 | -6.25% |  | Rhonda Meilani | P-314 | Ottinger | 6 | Lead | 91
| P-255 | Therapy practice evaluation | 40 | 3400 | 6800 | 3400 | 50% |  | Sherry Quam | P-255 | Ottinger | 3 | Associate | 80
| P-314 | Strategic planning | 35 | 2975 | 5500 | 2525 | 45.91% |  | Joe Shepard | G-131 | Hetzel | 2.7 | Associate | 79
| P-400 | New services development | 84 | 7140 | 7400 | 260 | 3.514% |  | Maya Gupta | P-245 | Ottinger | 3.4 | Associate | 92
| P-245 | Therapy analysis | 40 | 3400 | 7401 | 4001 | 54.06% |  | Jacob Fay | F-130 | Cisneros | 3.8 | Associate | 83
| F-125 | New revenue generation | 125 | 10625 | 10000 | -625 | -6.25% |  | Rosalie Dorne | H-305 | Mika | 5.1 | Lead | 75
| F-130 | Expense reduction | 95 | 8075 | 10000 | 1925 | 19.25% |  | Andre Patanka | G-240 | Hetzel | 4.8 | Lead | 90
| H-305 | Medical staff development | 40 | 3400 | 10200 | 6800 | 66.67% |  | Cam Wells | P-400 | Ottinger | 5.2 | Lead | 85
|  | Total | 584 | 49640 | 67801 | 18161 | 26.79%
| Average years of experience |  | 4.2778

## Consultants
Consultants
Name | Services | Manager | Years | Role | Eval Score
Kirk Deegan | F-125 | Cisneros | 4.5 |  | 88
Rhonda Meilani | P-314 | Ottinger | 6 |  | 91
Sherry Quam | P-255 | Ottinger | 3 |  | 80
Joe Shepard | G-131 | Hetzel | 2.7 |  | 79
Maya Gupta | P-245 | Ottinger | 3.4 |  | 92
Jacob Fay | F-130 | Cisneros | 3.8 |  | 83
Rosalie Dorne | H-305 | Mika | 5.1 |  | 75
Andre Patanka | G-240 | Hetzel | 4.8 |  | 90
Cam Wells | P-400 | Ottinger | 5.2 |  | 85

## Project Schedule
Professional Therapies System Upgrade
Project Schedule for Remaining Services
| G-131 | P-400 | F-125 | F-130 | H-305
Workdays | 10 | 12 | 5 | 14 | 15
Phase 2 | 2021-05-17 | 2021-05-21 | 2021-05-14 | 2021-05-16 | 2021-05-19
Phase 3 | 2021-06-01 | 2021-06-05 | 2021-05-29 | 2021-05-31 | 2021-06-03
Phase 4 | 2021-06-15 | 2021-06-19 | 2021-06-12 | 2021-06-14 | 2021-06-17
Phase 5 | 2021-06-29 | 2021-07-03 | 2021-06-26 | 2021-06-28 | 2021-07-01
Start date | 2021-05-14
Completion date | 2021-07-03
Formulas:
P-400 = [G-131]+4
F-125 = [G-131]-3
F-130 = [F-125]+2
H-305 = [G-131]+2